## Sheet1
SN | Activities | Plan start date | Owner | Time(hours) | Plan end date | Actual start Date | Actual end Date | Dependency | Comments
1 | Requirement gathering - meeting with client 1 | 2023-03-01 | BA team | 2 | 2023-03-01
2 | Requirement discussion internally-1 | 2023-03-01 | BA team | 3 | 2023-03-01
3 | Requirement gathering - meeting with client 2 | 2023-03-04 | BA team | 2 | 2023-03-04
4 | Requirement discussion internally-2 | 2023-03-04 | BA team | 2 | 2023-03-04
5 | Final Requirement Review with client - Artifact Requirment doc | 2023-03-10 | BA team | 2 | 2023-03-10
6 | Discuss at high level technology,release cities, Database, capacity, storage, CI/CD tools | 2023-03-11 | Dev, operations, DBAs, BA | 20 | 2023-03-20
7 | Identify major microservices | 2023-03-21 | Dev team | 10 | 2023-03-28
8 | Create use case for first two major micro service | 2023-03-29 | Dev | 5 | 2023-03-31
| Database selection and design data base objects and db modelling | 2023-03-21 | DB team | 20 | 2023-03-31
9 | Design microservices on the basis of use cases and rquirements | 2023-04-01 | Dev team | 5 | 2023-04-04
10 | Design Review - artifact Design doc | 2023-04-05 | Dev team | 2 | 2023-04-05
11 | Provisioning of cloud - for development | 2023-03-25 | Operations/dev | 10 | 2023-04-01
12 | DB modeling review and artifact DB design doc | 2023-04-01 | DB team | 5 | 2023-04-04
| Coding of microservices | 2023-04-07 | Dev team | 20 | 2023-04-11
13 | Kick off meetings with testing team on requirement and test strategy | 2023-04-01 | testing team | 10 | 2023-04-11
14 | code reviews/test plan reviews - Pseudo codes/test plan | 2023-04-11 | Dev/testing team | 10 | 2023-04-15
15 | Testing execution and review results | 2023-04-15 | testing team | 5 | 2023-04-20
16 | Deployment plan
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plan 15 mins stand up meeting everyday to track the progress
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of meeting may varies as the execution result varies